## Project_Name
No | Task | Assignee | Assign |  | Actual |  | Progress | Status | Remark
|  |  | Start Date | End Date | Start Date | End Date
1 | Layout (UI) | Khwar Nyo | 2021-11-08 | 09/11/2021: 12:00 PM (After Lunch)
2 | Student Data (UI) | Khwar Nyo | 2021-11-09 | 2021-11-09
3 | Student Dashboard (UI) | Khwar Nyo | 2021-11-10 | 2021-11-10
4 | Teacher Dashboard (UI) | Khwar Nyo | 2021-11-10 | 2021-11-10
5 | Login/ Register (UI) | Tyi Kyi | 2021-11-08 | 09/11/2021: 12:00 PM (After Lunch)
6 | Profile (UI) | Tyi Kyi | 2021-11-09 | 10/11/2021: 12:00 PM (After Lunch)
7 | Course (UI) | Htet Htet Aung | 2021-11-08 | 2021-11-08
8 | Course Details (UI) | Htet Htet Aung | 2021-11-09 | 2021-11-09
9 | Homework Student (UI) | Ye Zaw Aung | 2021-11-08 | 2021-11-08
10 | Homework Teacher (UI) | Ye Zaw Aung | 2021-11-09 | 2021-11-09
11 | Controller Route | Tyi Kyi
12 | Data Access Layer | Ye Zaw Aung
13 | Form Validation
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31